## Job Cost Sheet
CONSTRUCTION JOB COST SHEET
Job name
Client
Job address
Start date
Target completion
Contract amount
ESTIMATED COSTS
Cost code | Description | Labor | Materials | Subcontractors | Equipment & rental | Permits, dump & other | Row total
100 | Demo & disposal
200 | Rough carpentry / framing
300 | Plumbing
400 | Electrical
500 | HVAC
600 | Drywall & paint
700 | Tile & flooring
800 | Cabinets & countertops
900 | Fixtures & finish carpentry
1000 | Cleanup & punch list
TOTAL
ACTUAL COSTS
Cost code | Description | Labor | Materials | Subcontractors | Equipment & rental | Permits, dump & other | Row total
100 | Demo & disposal
200 | Rough carpentry / framing
300 | Plumbing
400 | Electrical
500 | HVAC
600 | Drywall & paint
700 | Tile & flooring
800 | Cabinets & countertops
900 | Fixtures & finish carpentry
1000 | Cleanup & punch list
TOTAL
SUMMARY — ESTIMATE vs. ACTUAL
Category | Estimated | Actual | Variance
Labor
Materials
Subcontractors
Equipment & rental
Permits, dump & other
Total cost
Contract amount
Gross profit
Margin
How to use: fill the ESTIMATED block when you bid, then update the ACTUAL block weekly as receipts, hours and sub invoices come in. The SUMMARY recalculates itself. Watch the Variance column — and compare percent spent against percent built, because a job that is 60% built and 85% spent has a problem you can still fix. Free from jobcostpro.online — not tax or accounting advice.

## Example - $42k Bathroom
CONSTRUCTION JOB COST SHEET
Job name | Primary bathroom remodel
Client | Sample client
Job address | Fort Worth, TX
Start date | 2026-01-06
Target completion | 2026-02-20
Contract amount | 42000
ESTIMATED COSTS
Cost code | Description | Labor | Materials | Subcontractors | Equipment & rental | Permits, dump & other | Row total
100 | Demo & disposal | 900 | 0 | 0 | 0 | 700
200 | Rough carpentry / framing | 1600 | 1200 | 0 | 200 | 0
300 | Plumbing | 0 | 0 | 3800 | 0 | 0
400 | Electrical | 0 | 0 | 1900 | 0 | 0
500 | HVAC | 0 | 0 | 600 | 0 | 0
600 | Drywall & paint | 1200 | 700 | 1200 | 0 | 0
700 | Tile & flooring | 2600 | 3400 | 0 | 400 | 0
800 | Cabinets & countertops | 1100 | 3300 | 0 | 0 | 0
900 | Fixtures & finish carpentry | 1000 | 1900 | 0 | 0 | 0
1000 | Cleanup & punch list | 600 | 0 | 0 | 400 | 700
TOTAL
ACTUAL COSTS
Cost code | Description | Labor | Materials | Subcontractors | Equipment & rental | Permits, dump & other | Row total
100 | Demo & disposal | 1150 | 0 | 0 | 0 | 850
200 | Rough carpentry / framing | 2050 | 1560 | 0 | 260 | 0
300 | Plumbing | 0 | 0 | 4600 | 0 | 0
400 | Electrical | 0 | 0 | 2350 | 0 | 0
500 | HVAC | 0 | 0 | 750 | 0 | 0
600 | Drywall & paint | 1450 | 890 | 1600 | 0 | 0
700 | Tile & flooring | 3200 | 4220 | 0 | 540 | 0
800 | Cabinets & countertops | 1350 | 4010 | 0 | 0 | 0
900 | Fixtures & finish carpentry | 1250 | 2780 | 0 | 0 | 0
1000 | Cleanup & punch list | 750 | 0 | 0 | 600 | 750
TOTAL
SUMMARY — ESTIMATE vs. ACTUAL
Category | Estimated | Actual | Variance
Labor
Materials
Subcontractors
Equipment & rental
Permits, dump & other
Total cost
Contract amount
Gross profit
Margin
How to use: fill the ESTIMATED block when you bid, then update the ACTUAL block weekly as receipts, hours and sub invoices come in. The SUMMARY recalculates itself. Watch the Variance column — and compare percent spent against percent built, because a job that is 60% built and 85% spent has a problem you can still fix. Free from jobcostpro.online — not tax or accounting advice.